{"text_format":"3","workbook":"xls","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"external_links":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":66,"n_cols":3,"rows_kept":66,"flags":["formulas_cached_only"]}
["[Project Name]"]
["Work Breakdown Structure"]
[]
[null,null,"Duration"]
[1,"Gather Requirements"]
[1.01,"Collect project ideas"]
[1.02,"Prioritize project ideas"]
[1.03,"Gather customer requirements and proposed solutions"]
[1.04,"Select and justify a project"]
[1.05,"Submit and approve the Request for Proposal (RFP)"]
[1.06,"Identify the project sponsor and project manager"]
[1.07,"Get the project team in place"]
[1.08,"Prepare the Requirements Document (RD)"]
[1.09,"Conduct project kickoff meeting"]
[{"v":1.1,"d":"1.10"},"Conduct project brainstorming meeting"]
[1.11,"Develop Statement of Scope (SOS)"]
[1.12,"Conduct work-breakdown structure meeting"]
[1.13,"Build Work Breakdown Structure (WBS)"]
[1.14,"Transfer WBS to Microsoft Project"]
[1.15,"Outline project plan"]
[1.16,"Assign resources to project plan tasks"]
[2,"Analysis"]
[2.01,"Create Entity Relationship Diagram (ERD)"]
[2.02,"Create Data Flow Diagram (DFD)"]
[2.03,"Define data dictionary"]
[2.04,"Perform object-oriented analysis"]
[3,"Design"]
[3.01,"Design data model"]
[3.02,"Write functional specifications"]
[3.03,"Design storyboards and/or prototypes"]
[3.04,"Write detailed design specifications"]
[3.05,"Write documentation plan"]
[3.06,"Write beta test plan"]
[3.07,"Write SQA test plan"]
[3.08,"Write SQA test cases"]
[3.09,"Write customer support plan"]
[{"v":3.1,"d":"3.10"},"Write training plan"]
[3.11,"Write risk management plan"]
[4,"Development"]
[4.01,"Code application components"]
[4.02,"Unit test"]
[4.03,"Integration test"]
[4.04,"Write documentation"]
[4.05,"Write training courseware"]
[5,"Test (Software Quality Assurance - SQA)"]
[5.01,"System test"]
[5.02,"Track defects"]
[5.03,"Regression test"]
[6,"Manage Release and Change"]
[6.01,"Configuration management"]
[6.02,"New full releases"]
[6.03,"Maintenance releases"]
[6.04,"Defect and enhancement tracking"]
[7,"Implementation"]
[7.01,"Install beta test system"]
[7.02,"Conduct beta tests"]
[7.03,"Track defects and report to customer support"]
[7.04,"Gather requirements for customizations"]
[7.05,"Analysis (gap between customizations & \"vanilla\")"]
[7.06,"Design"]
[7.07,"Install development system (GA release)"]
[7.08,"Implement/adapt Software"]
[7.09,"Unit test adaptations"]
[{"v":7.1,"d":"7.10"},"Integration test"]
[7.11,"Execute customer acceptance test procedure"]
[7.12,"Cutover development to production (pilot)"]